## Sheet1
Sprint Backlog Template

Backlog Item	Story Points	Responsible	Status	Original Estimate	Day 1	Day 2	Day 3	Day 4	Day 5	Sprint Review
User Story: As a student, I want to create an account so I can use the ride-sharing system.				16
Task 1: Plan MERN stack project structure				1	1
Task 2: Create backend and frontend projects				2	2					Sprint Burndown
Task 3: Implement Create Account backend API				5	3	2
Task 4: Troubleshoot MongoDB installation and server issues					3
Task 5: Implement Create Account React UI				5	1	3	3
Task 6: Connect frontend to backend API				3			3

User Story #2	1
Task				3	3	0.5	0.5	0	0	2
Task				3	5	5	1	1	1	0
Task				2	2	5	0	1	0	1
Task				5	5	9	5	1	0	1
User Story #3	5
Task				8	6	0	0	0	0	0
Task				3	1	3	3	3	0	0
Task				1.5	1	0.5	0.5	1	1	0
Task				2	0.5	0	0	0	0	3
User Story #4	8
Task				9	4	2	2	1	1	0
Task				6	6	3	3	3	1	1
Task				6	2	8	8	1	0	1
Task				0.5	0.5	0.5	0.5	0	0	0
User Story #5	3
Task				2	1	1	1	0.5	1	1
Task				6	6	6	0.5	3	9	0
Task				9	9	9	4	3	3	3
Task				0.5	0.5	0.5	1	0.5	0	1
Total				98.5	59.5	61	36	19	17	14

Create a Sprint Backlog in Smartsheet