## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
User Story: As a student, I want to create an account so I can use the ride-sharing system. | 8
Task: Develop the front-end user interface for the account creation form. |  |  |  | 7 | 5 | 3 | 0 | 0 | 0 | 0
Task: Implement back-end logic for account creation and user data storage |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task: Implement email domain validation (e.g., @uohyd.ac.in). |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task: Implement validation for required fields (name, student ID, email). |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
Task: Implement profile picture upload functionality.
Task: Develop test cases for all flows (normal, alternative, exceptions).
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
Total |  |  |  | 78 | 60 | 59 | 41 | 20 | 18 | 14
Create a Sprint Backlog in Smartsheet